## READ ME
Fracture Liaison Service (FLS) Implementation Plan (from Business Case approval)
Important - please read
Disclaimer:
This template is provided free by the Royal Osteoporosis Society as part of the Fracture Liaison Service Implementation Toolkit. This template does not represent the views of the Royal Osteoporosis Society. While every effort has been made to ensure that the information contained within this document is accurate and in full compliance with UK law and with best practice, at the time of writing, there is no guarantee as to the accuracy or reliability of the information contained herein and use of this template is entirely at the user’s risk. No liability whatsoever is accepted by the Royal Osteoporosis Society for its use or the data entered or contained within it.
This template
This plan is a template and will not cover all of the issues and situations that apply locally. You are encouraged to overwrite; to insert or delete rows; to add other information as you see fit. Not all of the tasks that are needed will be on the template and some that are may not be relevant in your locality. This resource has been created by the Royal Osteoporosis Society to help with the implementation of a fracture liaison service for the following purposes:
- to ensure all elements of the pathway are considered - both the clinical pathway and the patient support pathway
- to ensure all stakeholders are involved in the development and implementation of the Fracture Liaison Service
- to assist providers and commissioners to understand the timeframes for implementation
- to ensure monitoring and evaluation is built into the development of the Fracture Liaison Service
Important information
The tool and any data contained must be used in a way that is fully compliant with the policies on data security and records management in place in your organisation. Any information collected using this tool or stored within the tool should be properly backed up.
Every effort has been made to make sure that the information contained within the tool is accurate and is fully compliant with UK law and with best practice at the time of writing. Every effort has been made to assure the operational accuracy and reliability of the tool. There is no guarantee as to the accuracy of the information or the reliability of tool and use of this tool is entirely at the user’s risk and no liability whatsoever is accepted by the Royal Osteoporosis Society. The timeframes have been given as an estimation only and should be up-dated accordingly depending on your local policies and procedures.
Help
For help with using the tool please contact your the Royal Osteoporosis Society at fls@theros.org.uk
Reporting faults and suggesting improvements
If you find that there are problems with the tool or you wish to suggest improvements please contact the Royal Osteoporosis Society at fls@theros.org.uk
                v5 February 2021

## Implementation Plan
Fracture Liaison Service Implementation Plan (following Business Case agreement) | [5 empty] | Project Team | Initials | Role
Last updated by: Date: | [8 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
No | Activity | Lead | Other Involvement | Status | RAG | Actions / Comments / Issues | Start Date | End Date | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24
1 | Project Team (should have been part of business case development)
1.1.1 | Agree project team | [5 empty] | Week 1 | Week 1
1.1.2 | Agree Clinical Lead | [5 empty] | Week 1 | Week 1
1.1.3 | Agree Management lead | [5 empty] | Week 1 | Week 1
1.1.4 | Agree Commissioning Lead | [5 empty] | Week 1 | Week 1
1.1.5 | Agree DXA Lead | [5 empty] | Week 1 | Week 1
1.1.6 | Agree Patient Representative | [5 empty] | Week 1 | Week 4
1.1.7 | Agree Radiology Lead
1.1.8 | Agree Primary Care Lead
1.1.9 | Agree Lead from ED
1.2.1 | Orthopaedics/Rheumatology/Endocrinology colleagues
2 | Planning | [7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
2.1.1 | Agree timeframes | [5 empty] | Week 2 | Week 2
2.1.2 | Identify risks | [5 empty] | Week 2 | Week 2
2.1.3 | Agree Main Outcomes/KPIs | [5 empty] | Week 2 | Week 4
2.1.4 | Service Specification development | [5 empty] | Week 2 | Week 5
2.1.5 | Sign off Service Specification | [6 empty] | Week 5
2.1.6
2.1.7
2.1.8
2.1.9
3 | Resource Planning | [7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
3.1.1 | Design Recruitment advert | [5 empty] | Week 1 | Week 2
3.1.2 | Advertise resources required | [5 empty] | Week 2 | Week 5
3.1.3 | Agreement of interview panel | [5 empty] | Week 4 | Week 5
3.1.4 | Interview date | [6 empty] | Week 6
3.1.5 | Notice period for appointed staff |  |  |  |  | Depends on notice period of staff | Week 7 | Week 13
3.1.6 | Agree job plan for staff | [6 empty] | Week 7
3.1.7 | Book FLS specific training for new staff (ROS Fracture Prevention Practitioner Training: https://theros.org.uk/healthcare-professionals/courses-and-cpd/) | [6 empty] | Week 8
3.1.8 | Book in mandatory training/induction for new team | [6 empty] | Week 8
3.1.9
4 | Service Development | [7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
4.1.1 | Process map care pathway (including interdependencies with other services) |  |  |  |  | If possible involve the new staff | Week 2 | Week 4
4.1.2 | Process map the patient journey (including plans for newly diagnosed and patient education) |  |  |  |  | If possible involve the new staff | Week 2 | Week 4
4.1.3 | Agree local guidelines for standard bloods and DXA referral criteria | [5 empty] | Week 2 | Week 4
4.1.4 | Ensure agreement on clinic spaces |  |  |  |  | If possible involve the new staff | Week 2 | Week 4
4.1.5 | Draw up referral forms/protocols |  |  |  |  | If possible involve the new staff
4.1.5 | Draw up patient information materials |  |  |  |  | If possible involve the new staff | Week 2 | Week 4
4.1.6 | Send to all stakeholders for review |  |  |  |  | If possible involve the new staff | Week 5 | Week 6
4.1.7 | Finalise documents following stakeholder comments |  |  |  |  | If possible involve the new staff | Week 6 | Week 8
4.1.8 | FLN starts to identify and assess new patients |  |  |  |  | Depends on notice period | Week 16 | on-going
4.1.9 | FLN starts to identify and assess new vertebral fracture patients |  |  |  |  | Depends on local agreement
4.2.1
5 | Comms and Stakeholder engagement | [7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
5.1.1 | Acute Service Education/publicity Event | [6 empty] | Week 15
5.1.2 | Specific GP/Practice Nurse Education/publicity Event | [6 empty] | Week 15
5.1.3 | Patient Education/publicity Event for launch of service | [6 empty] | Week 15
5.1.4 | Engage with all secondary care clinicians (including orthopaedics, biochemists, pharmacy, rheumatologists, endocrinologists, fracture clinics, trauma co-ordinators, orthogeriatrician, medical/surgical teams and MSK and Radiology/DXA teams) | [5 empty] | Week 4 | Week 15
5.1.5 | Engage with local ROS support group (if available) | [6 empty] | Week 16
5.1.6 | Local media coverage | [6 empty] | Week 16
5.1.7 | Notify all referrers to service | [6 empty] | Week 16
5.1.8 | Notify all GPs | [6 empty] | Week 16
5.1.9 | Finalise patient information materials | [6 empty] | Week 16
5.2.1 | Issue referral forms/protocol | [6 empty] | Week 16
5.2.2 | Print/order patient information materials | [6 empty] | Week 15
5.2.3
5.2.4
6 | Monitoring | [7 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
6.1.1 | Register site on FLS Database (FLS-DB) and complete Facilities Audit |  |  |  |  | Depends on notice period of any new staff |  | Week 14
6.1.2 | Training to input on FLS-DB. Agree local up-load procedure for FLS-DB |  |  |  |  | Depends on notice period of any new staff |  | Week 14
6.1.3 | Commence Data Collection on local database and up-loading onto FLS-DB |  |  |  |  | Depends on notice period of any new staff | Week 17 | on-going
6.1.4 | Agree lead contract monitoring from CCG and FLS and arrange contract meetings |  |  |  |  | Depends on notice period of any new staff |  | Week 16
6.1.5 | Complete monthly/quarterly reports for KPIs |  |  |  |  | Depends on notice period of any new staff |  | Week 20
6.1.6 | Establish Patient feedback questionnaire and get feedback from patient representative |  |  |  |  | Depends on notice period of any new staff | Week 15 | Week 16
6.1.7 | Finalise patient feedback questionnaire |  |  |  |  | Depends on notice period of any new staff |  | Week 17
6.1.8
6.1.9
7 | [8 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
7.1.1
7.1.2
7.1.3
7.1.4
7.1.5
7.1.6
7.1.7
7.1.8
7.1.9
RAG :
RED: Milestone will not be met despite mitigating actions
AMBER: Mitigating actions instigated in order to meet milestone
GREEN: Milestone on track
C = Complete
IP = In progress
NS = Not Started
= suggested timeframe
Status :